## Slide 1: Merchant Payments
PI-23 – Mid PI Review

## Slide 2: Recap
Pillar 2: Increase adoption of Mojaloop
  Merchant Payments is an important use case
Transfers vs Payments:
  As far as the flow of funds is concerned both are same.
  However, unlike Transfers, Payments
    Are Transfers linked to delivery of goods/services.
    Are carried out in different modes (Online/Remote, Proximity)
    Are of different types (P2G, P2M, Utility Bills etc.)
The goal of this workstream is to
  Identify market needs and create necessary tools to support adoption of Mojaloop for Merchant payments.

## Slide 3: Progress since March 2023
PI-21
PI-22
PI-23
Workstream re-initiated
Identified Epics and Stories
Started design of UI/UX for Merchant Portal
Prioritized focus on Small merchants and Proximity Payments
Merchant onboarding & Merchant Registry (Oracle)
Development of Merchant Portal & Registry components (MVP Features)
End-end flow diagrams and documentation of functionality
Enhancement of Merchant Portal with priority features
DA Approval on design and interaction between Merchant Registry and Mojaloop.
Test Case automation and CICD Setup
Complete release Checklist for Beta Release so the components are ready for Production
Integrated Registry with Mojaloop ALS

## Slide 4: Mid-PI Progress
Enhancement – New features
Test Case Automation and CICD setup
Packaging – Getting the V1.0 ready for release and adoption by community.
Notes: DFSP onboarding
Adding new DFSP user
Activation new DFSP system
DFSP Admin privileges
Add new Merchant record
Registration save as draft
View record
Maker, checker roles
Revert record
Creating new user with operator and auditor roles
DFSP operator privileges
DFSP auditor privileges
Hub onboarding
Auto-disabling default hub super admin
Hub admin privileges
Disable enable
Create new user(DFSP admin, hub admin)
View all merchant record
Cannot approve, reject merchant record
Recapture
Forget password

## Slide 5: Enhancements – new features
New Features (targeted for PI-23) | Requirement Analysis | Technical Design | Development | Testing (automation)
Enhancements in User Management – Hub users | Done | Done | Done | Done
Enhancements in User Management - DFSP user creation UI | Done | Done | Done | Done
DFSP Onboarding | Done | Done | Done | Done
Merchant Self service onboarding | Done | In Progress | Not started (will be part of V1.1) | Not started
Allow Merchant to change DFSP on their own without changing Alias | Done | In Progress | Not started (will be part of V1.1) | Not started

## Slide 6: Document references
Documentation on Github
  https://github.com/mojaloop/merchant-payment-docs
Implementation Repository
  https://github.com/mojaloop/merchant-registry-svc

## Slide 7: Packaging for release
Release checklist - Out of 32 items, 22 items are done.
Test Case Automation and CICD is completed as part of this.
Remaining are mostly in progress or ready for review.
We are targeting the first release with updated documentation within February 2024.

## Slide 8: Target for March 2024
Release v1.0 in February and publish on Mojaloop Github
Roll out additional enhancements as an update V1.1
  Caveat – need developers to contribute on tasks in February

## Slide 9: Work pipeline
Priority Tasks -
  Complete release checklist
    Release packaging
    Security testing
  Functionality – backlog
    Merchant initiated onboarding request
    User/Role management UI + integration with OIDC provider
Design Tasks
  Bulk merchant onboarding support
  Adding 2FA on Portals
  Request to Pay – Merchant initiated request
Demo Lab Setup
  Setup a 24x7 demo lab with Customer and Merchant Apps for adopters to view and run end-end transactions

## Slide 10: Community Support required
Currently active members are from
  ThitsaWorks
  Paysys Labs
  iMoSys
Meeting schedule
  Development team
    Twice a week – 30-60 minutes session
  Workstream Update
    Every alternate Friday – 30 mins to 1 hour
We need more active participation of other members
  Developers
  DevOPS engineers – helping with CICD tasks
  QA/Testing person – Security testing
  Adopters – to give feedback on the functionality to be prioritized.

## Slide 11: Thank You

## Slide 12: Backup slides

## Slide 13: High level architecture
Mojaloop
ALS
Customer/Payer DFSP
Merchant
DFSP
Merchant Payment Tools
Merchant
Onboarding Portal
Merchant
Registry (Oracle)
USSD
APP
WEB
Alias - DFSP
Alias - Account

## Slide 14: High level architecture
Mojaloop
ALS
PH-EE
(Customer)
PH-EE
(Merchant)
Merchant Payment Tools
Merchant
Onboarding Portal
Merchant
Registry (Oracle)
USSD
APP
WEB
Alias - DFSP
Alias - Account
MIFOS
MIFOS

## Slide 15: High level architecture – Alternate
Mojaloop
ALS
Customer/Payer DFSP
Merchant
DFSP
Merchant Payment Tools
Merchant
Onboarding Portal
Merchant
Registry (Oracle)
PISP
(non-Bank)
APP
WEB

## Slide 16: Merchant Acquiring Portal
Designed for
  Hub Operator
  DFSP participating in scheme as Merchant DFSP
  Merchants
Features
  Merchant onboarding life cycle (Approval, Revert, Reject)
  Designed to support different types of Merchants
  Merchant QR generation
  Audit Logs
  Merchant initiated onboarding (WIP)
  Merchant feature – Change DFSP (WIP)

## Slide 17: Merchant Registry
Acts as a Central Oracle for Merchant Alias
  Centralized Alias generation (either DFSP provided or auto-generated)
  Holds Alias – DFSP mapping
  API based interface for to request addition in registry
    Merchant Onboarding Portal.
    Any DFSP participating in scheme.
  Interface with Mojaloop ALS
  Audit Logs

## Slide 18: Our universe of Payment use cases
Payee
Small shop
Large store
Mode
Proximity
Online/Remote
Type
Merchandise
Service (Utility)
Chain store
Government
Channels
USSD
Mobile App
Web
Different merchants have different needs.
Pay in a bank/mobile money account
Pay store-wise
Pay all North region in Bank “X” and South in Bank “Y”
Depending on channel and type of Payee business, important to consider how customer and merchant are notified that a payment is done and goods/service can be given.
How the Payer is interacting with Payee (Merchant) differs between Proximity and Online payments.
Implications on Fraud and Risk Management
Depending on type of payment, there may or may not be a Bill presentment prior to payment.
Contextual information about Payment needs to be exchanged.